## Annual Returns Register
Return Reference | Period Start | Period End | Annual Return Due Date | Status | Customer Name | Permit Reference | Permit Type | Condition Type | Permit Holder(s) | Industry | Activities | Locations | PRCP / no PRCP | 1. Change may affect ERC decision? | 2. EA for eligible resource activity? | 3. EA for ineligible resource activity without approved PRCP schedule? | 4. EA for ineligible Resource Activity for CSG? | Table 1 (1 Total Area ha) | Table 1 (1 Spatial Submitted) | Table 1 (2 Total Disturbance ha) | Table 1 (2 Spatial Submitted) | Table 1 (3 Total Rehab Certified ha) | Table 1 (3 Spatial Submitted) | Table 1 (4 Total Rehab Completed ha) | Table 1 (4 Spatial Submitted) | Table 1 (5 Total Rehab Commenced ha) | Table 1 (5 Spatial Submitted) | Table 1 (6 Area Disturbed ha) | Table 1 (6 Spatial Submitted) | Table 1 (7 Approved Progressive Certification ha) | Table 1 (7 Spatial Submitted) | Table 1 (8 Rehab not yet Approved ha) | Table 1 (8 Spatial Submitted) | Table 1 (9 Rehab Commenced ha) | Table 1 (9 Spatial Submitted) | Table 1 (10 Proposed Disturbance ha) | Table 1 (10 Spatial Submitted) | Table 1 (11 Rehab for Certification ha) | Table 1 (11 Spatial Submitted) | Table 1 (12 Rehab not for Certification ha) | Table 1 (12 Spatial Submitted) | Table 1 (13 Rehab to Commence ha) | Table 1 (13 Spatial Submitted) | 5. Has there been a change to the carrying out of the resource activity that may affect the estimated rehabilitation cost (ERC) decision for the activity? | 6. Has the required GIS Spatial information been submitted in accordance with an approved PRC Plan? | 7. Have you complied with your PRCP schedule? | 8. Have you complied with all other conditions imposed on the PRCP schedule? | 9. Are works related to any other rehabilitation or management milestones underway? | Table 2 (1 Total Area ha) | Table 2 (1 Spatial Submitted) | Table 2 (2 Total Disturbance ha) | Table 2 (2 Spatial Submitted) | Table 2 (3 Total Rehab Certified ha) | Table 2 (3 Spatial Submitted) | Table 2 (4 Total Rehab Completed ha) | Table 2 (4 Spatial Submitted) | Table 2 (5 Total Rehab Commenced ha) | Table 2 (5 Spatial Submitted) | Table 2 (6 Total Sufficient Improvement ha) | Table 2 (6 Spatial Submitted) | Table 2 (7 Total Improvement Commenced ha) | Table 2 (7 Spatial Submitted) | Table 2 (8 Area Disturbed ha) | Table 2 (8 Spatial Submitted) | Table 2 (9 Approved Progressive Certification ha) | Table 2 (9 Spatial Submitted) | Table 2 (10 Rehab not yet Approved ha) | Table 2 (10 Spatial Submitted) | Table 2 (11 Rehab Commenced ha) | Table 2 (11 Spatial Submitted) | Table 2 (12 Sufficient Improvement ha) | Table 2 (12 Spatial Submitted) | Table 2 (13 Improvement Commenced ha) | Table 2 (13 Spatial Submitted) | Table 2 (14 Proposed Disturbance ha) | Table 2 (14 Spatial Submitted) | Table 2 (15 Rehab for Certification ha) | Table 2 (15 Spatial Submitted) | Table 2 (16 Rehab not for Certification ha) | Table 2 (16 Spatial Submitted) | Table 2 (17 Rehab to Commence ha) | Table 2 (17 Spatial Submitted) | Table 2 (18 Proposed Sufficient Improvement ha) | Table 2 (18 Spatial Submitted) | Table 2 (19 Improvement to Commence ha) | Table 2 (19 Spatial Submitted) | Signatory Name | Signatory Position | Date
RET-100343220 | 2022-01-01 | 2022-12-31 | 2023-04-01 | Completed | Syntech Resources Pty Ltd | EPML00900113 | Resource Activity | Site-specific | SYNTECH RESOURCES PTY LTD; | Coal | Ancillary 63 - Sewage Treatment, 1(b-i) - Operating sewage treatment works, other than no-release works, with a total daily peak design capacity of more than 100 but not more than 1500EP if treated effluent is discharged from the works to an infiltration trench or through an irrigation scheme; Ancillary 31 - Mineral processing, 2(b) - Processing, in a year, the following quantities of mineral products, other than coke - more than 100,000t; Ancillary 60 - Waste disposal, 1(a) - Operating a facility for disposing of, in a year, the following quantity of waste mentioned in subsection (1)(a) - less than 50,000t; Schedule 3, 13 - Mining black coal; | ML50269 COLUMBOOLA 4415; ML50259 COLUMBOOLA 4415; ML50259 HOOKSWOOD 4415; ML50258 COLUMBOOLA 4415; ML50258 HOOKSWOOD 4415; ML50233 COLUMBOOLA 4415; ML50233 COLUMBOOLA 4415; ML50233 COLUMBOOLA 4415; ML50259 COLUMBOOLA 4415; ML50259 HOOKSWOOD 4415; ML50233 COLUMBOOLA 4415; ML50269 COLUMBOOLA 4415; ML50260 COLUMBOOLA 4415; ML50260 GOOMBI ; ML50260 CAMEBY 4413; ML50260 COLUMBOOLA 4415; ML50260 GOOMBI ; ML50260 CAMEBY 4413; ML50260 COLUMBOOLA 4415; ML50260 GOOMBI ; ML50260 CAMEBY 4413; ML50258 COLUMBOOLA 4415; ML50258 HOOKSWOOD 4415; ML50258 COLUMBOOLA 4415; ML50258 HOOKSWOOD 4415; ML50258 COLUMBOOLA 4415; ML50258 HOOKSWOOD 4415; ML50269 COLUMBOOLA 4415; ML50259 COLUMBOOLA 4415; ML50259 HOOKSWOOD 4415; ML50269 COLUMBOOLA 4415; ML50259 COLUMBOOLA 4415; ML50259 HOOKSWOOD 4415; ML50260 COLUMBOOLA 4415; ML50260 GOOMBI ; ML50260 CAMEBY 4413; | A resource activity with an approved (PRCP) schedule – Only complete sections 2 and 3 of this form. | [30 empty] | No | I/We have submitted GIS spatial information, which represents the onsite disturbance, rehabilitation and improvement within Table 2; Spatial information has been submitted via the department’s spatial information submission inbox - spatialsubmit@des.qld.gov.au.; GIS spatial information has been prepared in accordance with the department’s Guideline - Spatial Information Submission (ESR/2018/4337), specifically Attachment 2 - Annual returns – shapefile attributes and submission requirements.; I/We have provided a summary of the onsite disturbance and rehabilitation within Table 2; Yes | Yes | Yes | Yes | 6816.5500 | N/A | 793.8000 | Yes | 0.0000 | N/A | 157.1000 | Yes | 42.8000 | Yes | 0.0000 | N/A | 0.0000 | N/A | 49.3000 | Yes | 0.0000 | N/A | 0.0000 | N/A | 2.1000 | Yes | 0.0000 | N/A | 0.0000 | N/A | 130.4000 | Yes | 0.0000 | N/A | 28.1600 | Yes | 19.7000 | Yes | 0.0000 | N/A | 0.0000 | N/A | Les Merton | Environment & Community Superintendent | 29/03/2023

## Q7 Details
Return Reference | Period Start | Period End | Annual Return Due Date | Status | Permit Reference | Q7. Compliance with PRCP Schedule? | Q7. Compliant - Improvement Area | Q7. Compliant - Milestone Reference | Q7. Compliant - Area Required ha | Q7. Compliant - Area Completed ha | Q7. Compliant - Actions Taken | Q7. Compliant - Effectiveness | Q7. Non Compliant - Improvement Area | Q7. Non Compliant - Milestone Reference | Q7. Non Compliant - Details
RET-100343220 | 2022-01-01 | 2022-12-31 | 2023-04-01 | Completed | EPML00900113 | Yes | RA15 | RM1 | 2.00 | 2.00 | a) All services disconnected and decommissioned. b) Contaminated water (e.g. affected by hydrocarbons, brine, metals, etc.) is treated to ensure consistency with upstream water quality characteristics, or removed off site. c) All wastes removed from site and lawfully disposed. d) All infrastructure and water storages demolished and removed, unless agreed in writing by landholders and relevant agencies. e) All roads and access tracks removed and ripped to reduce compaction, unless agreed in writing by landholders and relevant agencies. | a) Completed - No services located in this area b) Compleetd - No contaminated water located in this area c) Completed - No waste located in this area or previously removed from area. d) Completed - No infrastructure or water storages located in this area e) Completed - All roads/access tracks removed and ripped in accordance with the milestone criteria
RET-100343220 | 2022-01-01 | 2022-12-31 | 2023-04-01 | Completed | EPML00900113 | Yes | RA15 | RM4 | 2.00 | 2.00 | a) All major earthworks completed. b) Stable landform and angle achieved (up to 10%, or up to 33% where rock mulch or other stabilisation controls are used). f) Landform recontoured to be sympathetic to the adjacent landforms. h) Contour or graded drains installed as per construction design. | a) Completed - All major earthworks completed b) Completed - All slopes less than 10% or have rock mulch applied. Landform stable. f) Competed - Landform contoured and sympathetic with adjacent landforms h) Completed - No contour or graded drains installed.
RET-100343220 | 2022-01-01 | 2022-12-31 | 2023-04-01 | Completed | EPML00900113 | Yes | RA15 | RM5 | 2.00 | 2.00 | b) Topsoil placed to a minimum thickness of 100 mm. c) Topsoil amelioration and fertilisation process completed using gypsum, chemical fertiliser and/or compost as required to reach target Total N: 1,500 milligrams per kilogram (mg/kg), and Total P: 200 mg/kg. d) Till to 100 mm depth to mix and incorporate soil ameliorants (but not deep enough to bring waste rock material to the surface). e) An assessment of soil health and suitability has been completed and confirms soil is suitable for target vegetation establishment. | b) Completed - Topsoil placed minimum 100mm thick and incorporated with rock mulch. c) Completed - Topsoil amelioration with gypsum and compost in accordance with milestone criteria d) Completed - Tilled to ensure ameliorants incorporated in accordance with the milestone criteria e) Completed
RET-100343220 | 2022-01-01 | 2022-12-31 | 2023-04-01 | Completed | EPML00900113 | Yes | RA11 | RM1 | 15.00 | 15.00 | a) All services disconnected and decommissioned. b) Contaminated water (e.g. affected by hydrocarbons, brine, metals, etc.) is treated to ensure consistency with upstream water quality characteristics, or removed off site. c) All wastes removed from site and lawfully disposed. d) All infrastructure and water storages demolished and removed, unless agreed in writing by landholders and relevant agencies. e) All roads and access tracks removed and ripped to reduce compaction, unless agreed in writing by landholders and relevant agencies. | a) Completed - No services located in this area b) Compleetd - No contaminated water located in this area c) Completed - No waste located in this area or previously removed from area. d) Completed - No infrastructure or water storages located in this area e) Completed - All roads/access tracks removed and ripped in accordance with the milestone criteria
RET-100343220 | 2022-01-01 | 2022-12-31 | 2023-04-01 | Completed | EPML00900113 | Yes | RA11 | RM2 | 15.00 | 15.00 | a) Detailed site investigation report, as required under the Environmental Protection Act 1994, completed. b) Contaminated materials (e.g. PCBs, Dioxins, Mercury, hydrocarbon contaminated soils) removed and appropriately disposed or remediated. c) Validation testing confirms that contaminated soils have been removed or remediated. d) A site suitability statement confirms the uses or activities for which the land is suitable, align to the approved PMLUs for the site. | N/A - No contaminated land or soils identified in this area
RET-100343220 | 2022-01-01 | 2022-12-31 | 2023-04-01 | Completed | EPML00900113 | Yes | RA11 | RM4 | 15.00 | 15.00 | a) All major earthworks completed. b) Stable landform and angle achieved (up to 10%, or up to 33% where rock mulch or other stabilisation controls are used). f) Landform recontoured to be sympathetic to the adjacent landforms. h) Contour or graded drains installed as per construction design. | a) Completed - All major earthworks completed b) Completed - All slopes less than 10%. Landform stable f) Competed - Landform contoured and sympathetic with adjacent landforms h) Completed - No contour or graded drains installed.
RET-100343220 | 2022-01-01 | 2022-12-31 | 2023-04-01 | Completed | EPML00900113 | Yes | RA2 | RM1 | 19.00 | 19.00 | a) All services disconnected and decommissioned. b) Contaminated water (e.g. affected by hydrocarbons, brine, metals, etc.) is treated to ensure consistency with upstream water quality characteristics, or removed off site. c) All wastes removed from site and lawfully disposed. d) All infrastructure and water storages demolished and removed, unless agreed in writing by landholders and relevant agencies. e) All roads and access tracks removed and ripped to reduce compaction, unless agreed in writing by landholders and relevant agencies. | a) Completed - No services located in this area b) Compleetd - No contaminated water located in this area c) Completed - No waste located in this area or previously removed from area. d) Completed - No infrastructure or water storages located in this area e) Completed - All roads/access tracks removed and ripped in accordance with the milestone criteria
RET-100343220 | 2022-01-01 | 2022-12-31 | 2023-04-01 | Completed | EPML00900113 | Yes | RA2 | RM4 | 19.00 | 19.00 | a) All major earthworks completed. b) Stable landform and angle achieved (up to 10%, or up to 33% where rock mulch or other stabilisation controls are used). e) Final elevation of out of pit waste rock emplacements are not higher than 45 m above the natural ground level. f) Landform recontoured to be sympathetic to the adjacent landforms. h) Contour or graded drains installed as per construction design. | a) Completed - All major earthworks completed b) Completed - All slopes less than 10%. Landform stable e) Completed - Highest elevation of landform is 3xx mAHD. Natural ground level 3xx mAHD measured at toe of the slope immediately north of the area. f) Competed - Landform contoured and sympathetic with adjacent landforms h) Completed - No contour or graded drains installed.
RET-100343220 | 2022-01-01 | 2022-12-31 | 2023-04-01 | Completed | EPML00900113 | Yes | RA2 | RA5 | 19.00 | 19.00 | a) Waste rock material ripped to a minimum of 300 mm depth. b) Topsoil placed to a minimum thickness of 100 mm. c) Topsoil amelioration and fertilisation process completed using gypsum, chemical fertiliser and/or compost as required to reach target Total N: 1,500 milligrams per kilogram (mg/kg), and Total P: 200 mg/kg. d) Till to 100 mm depth to mix and incorporate soil ameliorants (but not deep enough to bring waste rock material to the surface). e) An assessment of soil health and suitability has been completed and confirms soil is suitable for target vegetation establishment. | a) Completed - Waste rock ripped to minimum 300mm depth (see SOW - Rehabilitation Contract) b) Completed - Topsoil placed minimum 100mm thick (see SOW - Rehabilitation Contract) c) Completed - Topsoil amelioration and fertiliser and compost in accordance with milestone criteria d) Completed - Tilled to ensure ameliorants incorporated in accordance with the milestone criteria (ee SOW - Rehabilitation Contract) e) Completed - see report "Cameby Downs Mine: Vegetation Monitoring 2021, Landloch. October 2021"
RET-100343220 | 2022-01-01 | 2022-12-31 | 2023-04-01 | Completed | EPML00900113 | Yes | RA1 | RM1 | 130.00 | 130.00 | a) All services disconnected and decommissioned. b) Contaminated water (e.g. affected by hydrocarbons, brine, metals, etc.) is treated to ensure consistency with upstream water quality characteristics, or removed off site. c) All wastes removed from site and lawfully disposed. d) All infrastructure and water storages demolished and removed, unless agreed in writing by landholders and relevant agencies. e) All roads and access tracks removed and ripped to reduce compaction, unless agreed in writing by landholders and relevant agencies. | a) Completed - No services located in this area b) Completed - No contaminated water located in this area c) Completed - No waste located in this area . d) Completed - No infrastructure or water storages located in this area e) Completed - All roads/access tracks removed and ripped in accordance with the milestone criteria
RET-100343220 | 2022-01-01 | 2022-12-31 | 2023-04-01 | Completed | EPML00900113 | Yes | RA1 | RM4 | 130.00 | 130.00 | a) All major earthworks completed. b) Stable landform and angle achieved (up to 10%, or up to 33% where rock mulch or other stabilisation controls are used). e) Final elevation of out of pit waste rock emplacements are not higher than 45 m above the natural ground level. f) Landform recontoured to be sympathetic to the adjacent landforms. h) Contour or graded drains installed as per construction design. | a) Completed - All major earthworks completed b) Completed - All slopes less than 10%. Landform stable e) Completed - Highest elevation of landform is 367.53 mAHD. Natural ground level 360.42 mAHD measured at toe of the slope in underdisturbed area immediately north of the area. f) Competed - Landform contoured and sympathetic with adjacent landforms h) Completed - No contour or graded drains installed.
RET-100343220 | 2022-01-01 | 2022-12-31 | 2023-04-01 | Completed | EPML00900113 | Yes | RA1 | RM5 | 130.00 | 130.00 | a) Waste rock material ripped to a minimum of 300 mm depth. b) Topsoil placed to a minimum thickness of 100 mm. c) Topsoil amelioration and fertilisation process completed using gypsum, chemical fertiliser and/or compost as required to reach target Total N: 1,500 milligrams per kilogram (mg/kg), and Total P: 200 mg/kg. d) Till to 100 mm depth to mix and incorporate soil ameliorants (but not deep enough to bring waste rock material to the surface). e) An assessment of soil health and suitability has been completed and confirms soil is suitable for target vegetation establishment. | a) Completed - Waste rock ripped to minimum 300mm depth (see SOW - Rehabilitation Contract) b) Completed - Topsoil placed minimum 100mm thick (see SOW - Rehabilitation Contract) c) Completed - Topsoil amelioration and fertiliser and compost in accordance with milestone criteria d) Completed - Tilled to ensure ameliorants incorporated in accordance with the milestone criteria (ee SOW - Rehabilitation Contract) e) Completed - see report "Cameby Downs Mine: Vegetation Monitoring 2021, Landloch. October 2021"

## Q8 Details
Return Reference | Period Start | Period End | Annual Return Due Date | Status | Permit Reference | Q8. Compliance with other conditions of PRCP? | Q8. Non Compliant - Condition Number | Q8. Non Compliant - Details
RET-100343220 | 2022-01-01 | 2022-12-31 | 2023-04-01 | Completed | EPML00900113 | Yes

## Q9 Details
Return Reference | Period Start | Period End | Annual Return Due Date | Status | Permit Reference | Q9. Other works underway? | Q9. Underway - Improvement Area | Q9. Underway - Milestone Reference | Q9. Underway - Completion Date | Q9. Underway - Area Completed ha | Q9. Underway - Actions Taken | Q9. Underway - Effectiveness
RET-100343220 | 2022-01-01 | 2022-12-31 | 2023-04-01 | Completed | EPML00900113 | Yes | RA1 | RM6 | Dec 10 2023 12:00AM | 130.00 | a) Topsoil ripped no more than three months later than placement. b) Till along the contour with a tined implement with tine spacing no greater than 0.5 m. c) Direct seeding of cover crop and pasture species completed (rates as specified in Table 3-6 of Revegetation Plan version 2, dated 23/06/2021). d) Selection of pasture grass species are consistent with designated vegetation reference sites and include a combination of pasture species detailed in ‘Table 20 Revegetation Species’ in the PRC Planning Part, version 4 (April 2022). | a) Completed - topsoil ripped within 3 months of placement b) Compleetd - topsoil ripped with grader tynes with spacing no grater than 0.5m c) Complete - direct seeded with suitable species at specified rates per Table 3-6 d) Complete - direct seeded with suitable species at specified rates per Table 20