## Annual Returns Register
Return Reference | Period Start | Period End | Annual Return Due Date | Status | Customer Name | Permit Reference | Permit Type | Condition Type | Permit Holder(s) | Industry | Activities | Locations | PRCP / no PRCP | 1. Change may affect ERC decision? | 2. EA for eligible resource activity? | 3. EA for ineligible resource activity without approved PRCP schedule? | 4. EA for ineligible Resource Activity for CSG? | Table 1 (1 Total Area ha) | Table 1 (1 Spatial Submitted) | Table 1 (2 Total Disturbance ha) | Table 1 (2 Spatial Submitted) | Table 1 (3 Total Rehab Certified ha) | Table 1 (3 Spatial Submitted) | Table 1 (4 Total Rehab Completed ha) | Table 1 (4 Spatial Submitted) | Table 1 (5 Total Rehab Commenced ha) | Table 1 (5 Spatial Submitted) | Table 1 (6 Area Disturbed ha) | Table 1 (6 Spatial Submitted) | Table 1 (7 Approved Progressive Certification ha) | Table 1 (7 Spatial Submitted) | Table 1 (8 Rehab not yet Approved ha) | Table 1 (8 Spatial Submitted) | Table 1 (9 Rehab Commenced ha) | Table 1 (9 Spatial Submitted) | Table 1 (10 Proposed Disturbance ha) | Table 1 (10 Spatial Submitted) | Table 1 (11 Rehab for Certification ha) | Table 1 (11 Spatial Submitted) | Table 1 (12 Rehab not for Certification ha) | Table 1 (12 Spatial Submitted) | Table 1 (13 Rehab to Commence ha) | Table 1 (13 Spatial Submitted) | 5. Has there been a change to the carrying out of the resource activity that may affect the estimated rehabilitation cost (ERC) decision for the activity? | 6. Has the required GIS Spatial information been submitted in accordance with an approved PRC Plan? | 7. Have you complied with your PRCP schedule? | 8. Have you complied with all other conditions imposed on the PRCP schedule? | 9. Are works related to any other rehabilitation or management milestones underway? | Table 2 (1 Total Area ha) | Table 2 (1 Spatial Submitted) | Table 2 (2 Total Disturbance ha) | Table 2 (2 Spatial Submitted) | Table 2 (3 Total Rehab Certified ha) | Table 2 (3 Spatial Submitted) | Table 2 (4 Total Rehab Completed ha) | Table 2 (4 Spatial Submitted) | Table 2 (5 Total Rehab Commenced ha) | Table 2 (5 Spatial Submitted) | Table 2 (6 Total Sufficient Improvement ha) | Table 2 (6 Spatial Submitted) | Table 2 (7 Total Improvement Commenced ha) | Table 2 (7 Spatial Submitted) | Table 2 (8 Area Disturbed ha) | Table 2 (8 Spatial Submitted) | Table 2 (9 Approved Progressive Certification ha) | Table 2 (9 Spatial Submitted) | Table 2 (10 Rehab not yet Approved ha) | Table 2 (10 Spatial Submitted) | Table 2 (11 Rehab Commenced ha) | Table 2 (11 Spatial Submitted) | Table 2 (12 Sufficient Improvement ha) | Table 2 (12 Spatial Submitted) | Table 2 (13 Improvement Commenced ha) | Table 2 (13 Spatial Submitted) | Table 2 (14 Proposed Disturbance ha) | Table 2 (14 Spatial Submitted) | Table 2 (15 Rehab for Certification ha) | Table 2 (15 Spatial Submitted) | Table 2 (16 Rehab not for Certification ha) | Table 2 (16 Spatial Submitted) | Table 2 (17 Rehab to Commence ha) | Table 2 (17 Spatial Submitted) | Table 2 (18 Proposed Sufficient Improvement ha) | Table 2 (18 Spatial Submitted) | Table 2 (19 Improvement to Commence ha) | Table 2 (19 Spatial Submitted) | Signatory Name | Signatory Position | Date
RET-100043082 | 2020-01-01 | 2020-12-31 | 2021-04-01 | Completed | QGC PTY LIMITED | EPPG00797813 | Resource Activity | Site-specific | QGC PTY LIMITED; CNOOC Coal Seam Gas Company Pty Ltd; MIDOCEAN QCLNG PTY LTD; BG INTERNATIONAL LIMITED; AUSTRALIA PACIFIC LNG PTY LIMITED; | Petroleum and Gas | Ancillary 62 - Resource recovery and transfer facility operation, 1(c) - Operating a facility for receiving and sorting, dismantling, baling or temporarily storing category 2 regulated waste; Ancillary 62 - Resource recovery and transfer facility operation, 1(d) - Operating a facility for receiving and sorting, dismantling, baling or temporarily storing category 1 regulated waste; Ancillary 62 - Resource recovery and transfer facility operation, 1(b) - Operating a facility for receiving and sorting, dismantling, baling or temporarily storing general waste; Ancillary 63 - Sewage Treatment, 1(b-i) - Operating sewage treatment works, other than no-release works, with a total daily peak design capacity of more than 100 but not more than 1500EP if treated effluent is discharged from the works to an infiltration trench or through an irrigation scheme; Ancillary 57 - Regulated Waste Transport, Transporting regulated waste; Ancillary 15 - Fuel burning, Using fuel burning equipment that is capable of burning at least 500kg of fuel in an hour; Schedule 3, 08 - A petroleum or GHG storage activity, other than items 1 to 7, that includes an activity from Schedule 2 with an AES; Schedule 3, 05 - Constructing a new pipeline of more than 150km under a petroleum authority; Schedule 3, 03 - A petroleum activity that is likely to have a significant impact on a category A or B Environmentally Sensitive Area; Schedule 3, 06 - A petroleum activity carried out on a site containing a high hazard dam or a significant hazard dam; Ancillary 60 - Waste disposal, 2(h) - Operating a facility for disposing of, in a year, the following quantity of waste mentioned in subsection (1)(b) - more than 200,000t; | PFL19 KUMBARILLA 4405; PFL19 KUMBARILLA 4405; PFL19 KUMBARILLA 4405; PFL19 KUMBARILLA 4405; PFL19 KUMBARILLA 4405; PFL19 KUMBARILLA 4405; PFL19 KUMBARILLA 4405; PFL19 KUMBARILLA 4405; PFL19 KUMBARILLA 4405; PFL19 KUMBARILLA 4405; PFL19 KUMBARILLA 4405; ATP648 CECIL PLAINS 4407; ATP648 MONTROSE 4370; ATP648 GRASSDALE 4405; ATP648 GORANBA 4421; ATP648 MACALISTER 4406; ATP648 RANGES BRIDGE 4405; ATP648 WIEAMBILLA 4413; ATP648 THE GUMS 4406; ATP648 MARMADUA 4405; ATP648 HALLIFORD ; ATP648 TARA 4421; ATP648 BEELBEE ; ATP648 WERANGA 4405; ATP648 KOGAN 4406; ATP648 KUMBARILLA 4405; ATP648 DUCKLO 4405; ATP648 CECIL PLAINS 4407; ATP648 MONTROSE 4370; ATP648 GRASSDALE 4405; ATP648 GORANBA 4421; ATP648 MACALISTER 4406; ATP648 RANGES BRIDGE 4405; ATP648 WIEAMBILLA 4413; ATP648 THE GUMS 4406; ATP648 MARMADUA 4405; ATP648 HALLIFORD ; ATP648 TARA 4421; ATP648 BEELBEE ; ATP648 WERANGA 4405; ATP648 KOGAN 4406; ATP648 KUMBARILLA 4405; ATP648 DUCKLO 4405; ATP648 CECIL PLAINS 4407; ATP648 MONTROSE 4370; ATP648 GRASSDALE 4405; ATP648 GORANBA 4421; ATP648 MACALISTER 4406; ATP648 RANGES BRIDGE 4405; ATP648 WIEAMBILLA 4413; ATP648 THE GUMS 4406; ATP648 MARMADUA 4405; ATP648 HALLIFORD ; ATP648 TARA 4421; ATP648 BEELBEE ; ATP648 WERANGA 4405; ATP648 KOGAN 4406; ATP648 KUMBARILLA 4405; ATP648 DUCKLO 4405; PL466 WERANGA 4405; PL466 KUMBARILLA 4405; PL466 WERANGA 4405; PL466 KUMBARILLA 4405; PL466 WERANGA 4405; PL466 KUMBARILLA 4405; PL466 WERANGA 4405; PL466 KUMBARILLA 4405; ATP648 CECIL PLAINS 4407; ATP648 MONTROSE 4370; ATP648 GRASSDALE 4405; ATP648 GORANBA 4421; ATP648 MACALISTER 4406; ATP648 RANGES BRIDGE 4405; ATP648 WIEAMBILLA 4413; ATP648 THE GUMS 4406; ATP648 MARMADUA 4405; ATP648 HALLIFORD ; ATP648 TARA 4421; ATP648 BEELBEE ; ATP648 WERANGA 4405; ATP648 KOGAN 4406; ATP648 KUMBARILLA 4405; ATP648 DUCKLO 4405; ATP648 CECIL PLAINS 4407; ATP648 MONTROSE 4370; ATP648 GRASSDALE 4405; ATP648 GORANBA 4421; ATP648 MACALISTER 4406; ATP648 RANGES BRIDGE 4405; ATP648 WIEAMBILLA 4413; ATP648 THE GUMS 4406; ATP648 MARMADUA 4405; ATP648 HALLIFORD ; ATP648 TARA 4421; ATP648 BEELBEE ; ATP648 WERANGA 4405; ATP648 KOGAN 4406; ATP648 KUMBARILLA 4405; ATP648 DUCKLO 4405; ATP648 CECIL PLAINS 4407; ATP648 MONTROSE 4370; ATP648 GRASSDALE 4405; ATP648 GORANBA 4421; ATP648 MACALISTER 4406; ATP648 RANGES BRIDGE 4405; ATP648 WIEAMBILLA 4413; ATP648 THE GUMS 4406; ATP648 MARMADUA 4405; ATP648 HALLIFORD ; ATP648 TARA 4421; ATP648 BEELBEE ; ATP648 WERANGA 4405; ATP648 KOGAN 4406; ATP648 KUMBARILLA 4405; ATP648 DUCKLO 4405; ATP648 CECIL PLAINS 4407; ATP648 MONTROSE 4370; ATP648 GRASSDALE 4405; ATP648 GORANBA 4421; ATP648 MACALISTER 4406; ATP648 RANGES BRIDGE 4405; ATP648 WIEAMBILLA 4413; ATP648 THE GUMS 4406; ATP648 MARMADUA 4405; ATP648 HALLIFORD ; ATP648 TARA 4421; ATP648 BEELBEE ; ATP648 WERANGA 4405; ATP648 KOGAN 4406; ATP648 KUMBARILLA 4405; ATP648 DUCKLO 4405; PL466 WERANGA 4405; PL466 KUMBARILLA 4405; PL466 WERANGA 4405; PL466 KUMBARILLA 4405; PL466 WERANGA 4405; PL466 KUMBARILLA 4405; PL466 WERANGA 4405; PL466 KUMBARILLA 4405; PL466 WERANGA 4405; PL466 KUMBARILLA 4405; PL466 WERANGA 4405; PL466 KUMBARILLA 4405; PL466 WERANGA 4405; PL466 KUMBARILLA 4405; PL474 HALLIFORD ; PL474 WERANGA 4405; PL474 KUMBARILLA 4405; PL474 MARMADUA 4405; PL474 HALLIFORD ; PL474 WERANGA 4405; PL474 KUMBARILLA 4405; PL474 MARMADUA 4405; PL474 HALLIFORD ; PL474 WERANGA 4405; PL474 KUMBARILLA 4405; PL474 MARMADUA 4405; PL474 HALLIFORD ; PL474 WERANGA 4405; PL474 KUMBARILLA 4405; PL474 MARMADUA 4405; PL474 HALLIFORD ; PL474 WERANGA 4405; PL474 KUMBARILLA 4405; PL474 MARMADUA 4405; PL474 HALLIFORD ; PL474 WERANGA 4405; PL474 KUMBARILLA 4405; PL474 MARMADUA 4405; PL474 HALLIFORD ; PL474 WERANGA 4405; PL474 KUMBARILLA 4405; PL474 MARMADUA 4405; PL474 HALLIFORD ; PL474 WERANGA 4405; PL474 KUMBARILLA 4405; PL474 MARMADUA 4405; PL474 HALLIFORD ; PL474 WERANGA 4405; PL474 KUMBARILLA 4405; PL474 MARMADUA 4405; PL474 HALLIFORD ; PL474 WERANGA 4405; PL474 KUMBARILLA 4405; PL474 MARMADUA 4405; PL474 HALLIFORD ; PL474 WERANGA 4405; PL474 KUMBARILLA 4405; PL474 MARMADUA 4405; ATP648 CECIL PLAINS 4407; ATP648 MONTROSE 4370; ATP648 GRASSDALE 4405; ATP648 GORANBA 4421; ATP648 MACALISTER 4406; ATP648 RANGES BRIDGE 4405; ATP648 WIEAMBILLA 4413; ATP648 THE GUMS 4406; ATP648 MARMADUA 4405; ATP648 HALLIFORD ; ATP648 TARA 4421; ATP648 BEELBEE ; ATP648 WERANGA 4405; ATP648 KOGAN 4406; ATP648 KUMBARILLA 4405; ATP648 DUCKLO 4405; ATP648 CECIL PLAINS 4407; ATP648 MONTROSE 4370; ATP648 GRASSDALE 4405; ATP648 GORANBA 4421; ATP648 MACALISTER 4406; ATP648 RANGES BRIDGE 4405; ATP648 WIEAMBILLA 4413; ATP648 THE GUMS 4406; ATP648 MARMADUA 4405; ATP648 HALLIFORD ; ATP648 TARA 4421; ATP648 BEELBEE ; ATP648 WERANGA 4405; ATP648 KOGAN 4406; ATP648 KUMBARILLA 4405; ATP648 DUCKLO 4405; ATP648 CECIL PLAINS 4407; ATP648 MONTROSE 4370; ATP648 GRASSDALE 4405; ATP648 GORANBA 4421; ATP648 MACALISTER 4406; ATP648 RANGES BRIDGE 4405; ATP648 WIEAMBILLA 4413; ATP648 THE GUMS 4406; ATP648 MARMADUA 4405; ATP648 HALLIFORD ; ATP648 TARA 4421; ATP648 BEELBEE ; ATP648 WERANGA 4405; ATP648 KOGAN 4406; ATP648 KUMBARILLA 4405; ATP648 DUCKLO 4405; ATP648 CECIL PLAINS 4407; ATP648 MONTROSE 4370; ATP648 GRASSDALE 4405; ATP648 GORANBA 4421; ATP648 MACALISTER 4406; ATP648 RANGES BRIDGE 4405; ATP648 WIEAMBILLA 4413; ATP648 THE GUMS 4406; ATP648 MARMADUA 4405; ATP648 HALLIFORD ; ATP648 TARA 4421; ATP648 BEELBEE ; ATP648 WERANGA 4405; ATP648 KOGAN 4406; ATP648 KUMBARILLA 4405; ATP648 DUCKLO 4405; PL1025 KOGAN 4406; PL1025 KOGAN 4406; PL274 HALLIFORD ; PL274 HALLIFORD ; PL274 HALLIFORD ; PL279 GRASSDALE 4405; PL279 HALLIFORD ; PL279 KUMBARILLA 4405; PL279 DUCKLO 4405; PL279 GRASSDALE 4405; PL279 HALLIFORD ; PL279 KUMBARILLA 4405; PL279 DUCKLO 4405; PL279 GRASSDALE 4405; PL279 HALLIFORD ; PL279 KUMBARILLA 4405; PL279 DUCKLO 4405; PL279 GRASSDALE 4405; PL279 HALLIFORD ; PL279 KUMBARILLA 4405; PL279 DUCKLO 4405; PL279 GRASSDALE 4405; PL279 HALLIFORD ; PL279 KUMBARILLA 4405; PL279 DUCKLO 4405; PL279 GRASSDALE 4405; PL279 HALLIFORD ; PL279 KUMBARILLA 4405; PL279 DUCKLO 4405; PL279 GRASSDALE 4405; PL279 HALLIFORD ; PL279 KUMBARILLA 4405; PL279 DUCKLO 4405; PL279 GRASSDALE 4405; PL279 HALLIFORD ; PL279 KUMBARILLA 4405; PL279 DUCKLO 4405; PL279 GRASSDALE 4405; PL279 HALLIFORD ; PL279 KUMBARILLA 4405; PL279 DUCKLO 4405; PL279 GRASSDALE 4405; PL279 HALLIFORD ; PL279 KUMBARILLA 4405; PL279 DUCKLO 4405; PL279 GRASSDALE 4405; PL279 HALLIFORD ; PL279 KUMBARILLA 4405; PL279 DUCKLO 4405; PL273 BEELBEE ; PL273 WERANGA 4405; PL273 KOGAN 4406; PL273 KUMBARILLA 4405; PL273 BEELBEE ; PL273 WERANGA 4405; PL273 KOGAN 4406; PL273 KUMBARILLA 4405; PL273 BEELBEE ; PL273 WERANGA 4405; PL273 KOGAN 4406; PL273 KUMBARILLA 4405; PL273 BEELBEE ; PL273 WERANGA 4405; PL273 KOGAN 4406; PL273 KUMBARILLA 4405; PL273 BEELBEE ; PL273 WERANGA 4405; PL273 KOGAN 4406; PL273 KUMBARILLA 4405; PL273 BEELBEE ; PL273 WERANGA 4405; PL273 KOGAN 4406; PL273 KUMBARILLA 4405; PL273 BEELBEE ; PL273 WERANGA 4405; PL273 KOGAN 4406; PL273 KUMBARILLA 4405; PL273 BEELBEE ; PL273 WERANGA 4405; PL273 KOGAN 4406; PL273 KUMBARILLA 4405; PL273 BEELBEE ; PL273 WERANGA 4405; PL273 KOGAN 4406; PL273 KUMBARILLA 4405; PL273 BEELBEE ; PL273 WERANGA 4405; PL273 KOGAN 4406; PL273 KUMBARILLA 4405; PL273 BEELBEE ; PL273 WERANGA 4405; PL273 KOGAN 4406; PL273 KUMBARILLA 4405; PL275 DUCKLO 4405; PL275 RANGES BRIDGE 4405; PL275 BEELBEE ; PL275 WERANGA 4405; PL275 KOGAN 4406; PL275 KUMBARILLA 4405; PL275 DUCKLO 4405; PL275 RANGES BRIDGE 4405; PL275 BEELBEE ; PL275 WERANGA 4405; PL275 KOGAN 4406; PL275 KUMBARILLA 4405; PL275 DUCKLO 4405; PL275 RANGES BRIDGE 4405; PL275 BEELBEE ; PL275 WERANGA 4405; PL275 KOGAN 4406; PL275 KUMBARILLA 4405; PL275 DUCKLO 4405; PL275 RANGES BRIDGE 4405; PL275 BEELBEE ; PL275 WERANGA 4405; PL275 KOGAN 4406; PL275 KUMBARILLA 4405; PL275 DUCKLO 4405; PL275 RANGES BRIDGE 4405; PL275 BEELBEE ; PL275 WERANGA 4405; PL275 KOGAN 4406; PL275 KUMBARILLA 4405; PL275 DUCKLO 4405; PL275 RANGES BRIDGE 4405; PL275 BEELBEE ; PL275 WERANGA 4405; PL275 KOGAN 4406; PL275 KUMBARILLA 4405; PL275 DUCKLO 4405; PL275 RANGES BRIDGE 4405; PL275 BEELBEE ; PL275 WERANGA 4405; PL275 KOGAN 4406; PL275 KUMBARILLA 4405; PL275 DUCKLO 4405; PL275 RANGES BRIDGE 4405; PL275 BEELBEE ; PL275 WERANGA 4405; PL275 KOGAN 4406; PL275 KUMBARILLA 4405; PL275 DUCKLO 4405; PL275 RANGES BRIDGE 4405; PL275 BEELBEE ; PL275 WERANGA 4405; PL275 KOGAN 4406; PL275 KUMBARILLA 4405; PL275 DUCKLO 4405; PL275 RANGES BRIDGE 4405; PL275 BEELBEE ; PL275 WERANGA 4405; PL275 KOGAN 4406; PL275 KUMBARILLA 4405; PL275 DUCKLO 4405; PL275 RANGES BRIDGE 4405; PL275 BEELBEE ; PL275 WERANGA 4405; PL275 KOGAN 4406; PL275 KUMBARILLA 4405; PL1025 KOGAN 4406; PL1025 KOGAN 4406; PL1025 KOGAN 4406; PL1025 KOGAN 4406; PL1025 KOGAN 4406; PL1025 KOGAN 4406; PL1025 KOGAN 4406; PL1025 KOGAN 4406; PL1025 KOGAN 4406; PL274 HALLIFORD ; PL274 HALLIFORD ; PL274 HALLIFORD ; PL274 HALLIFORD ; PL274 HALLIFORD ; PL274 HALLIFORD ; PL274 HALLIFORD ; PL274 HALLIFORD ; |  | No |  | I/We have submitted GIS spatial information, which represents the onsite disturbance and rehabilitation within Table 1.; Spatial information has been submitted via the department’s spatial information submission inbox - spatialsubmit@des.qld.gov.au.; GIS spatial information has been prepared in accordance with the department’s Guideline - Spatial Information Submission (ESR/2018/4337), specifically Attachment 2 - Annual returns – shapefile attributes and submission requirements.; I/We have provided a summary of the onsite disturbance and rehabilitation within Table 1.; Yes |  | 92682.4200 | N/A | 1053.0700 | N/A | 0.0000 | N/A |  |  | 2207.4800 | N/A | 82.7800 | N/A | 0.0000 | N/A |  | N/A | 48.9900 |  | 0.0000 |  | 0.0000 | N/A | 0.0000 | N/A | 0.0000 | N/A | [43 empty] | Patrick Carroll | QGC Environment Operations Manager | 01/04/2021

## Q7 Details
Return Reference | Period Start | Period End | Annual Return Due Date | Status | Permit Reference | Q7. Compliance with PRCP Schedule? | Q7. Compliant - Improvement Area | Q7. Compliant - Milestone Reference | Q7. Compliant - Area Required ha | Q7. Compliant - Area Completed ha | Q7. Compliant - Actions Taken | Q7. Compliant - Effectiveness | Q7. Non Compliant - Improvement Area | Q7. Non Compliant - Milestone Reference | Q7. Non Compliant - Details

## Q8 Details
Return Reference | Period Start | Period End | Annual Return Due Date | Status | Permit Reference | Q8. Compliance with other conditions of PRCP? | Q8. Non Compliant - Condition Number | Q8. Non Compliant - Details

## Q9 Details
Return Reference | Period Start | Period End | Annual Return Due Date | Status | Permit Reference | Q9. Other works underway? | Q9. Underway - Improvement Area | Q9. Underway - Milestone Reference | Q9. Underway - Completion Date | Q9. Underway - Area Completed ha | Q9. Underway - Actions Taken | Q9. Underway - Effectiveness