## Annual Returns Register
Return Reference | Period Start | Period End | Annual Return Due Date | Status | Customer Name | Permit Reference | Permit Type | Condition Type | Permit Holder(s) | Industry | Activities | Locations | PRCP / no PRCP | 1. Change may affect ERC decision? | 2. EA for eligible resource activity? | 3. EA for ineligible resource activity without approved PRCP schedule? | 4. EA for ineligible Resource Activity for CSG? | Table 1 (1 Total Area ha) | Table 1 (1 Spatial Submitted) | Table 1 (2 Total Disturbance ha) | Table 1 (2 Spatial Submitted) | Table 1 (3 Total Rehab Certified ha) | Table 1 (3 Spatial Submitted) | Table 1 (4 Total Rehab Completed ha) | Table 1 (4 Spatial Submitted) | Table 1 (5 Total Rehab Commenced ha) | Table 1 (5 Spatial Submitted) | Table 1 (6 Area Disturbed ha) | Table 1 (6 Spatial Submitted) | Table 1 (7 Approved Progressive Certification ha) | Table 1 (7 Spatial Submitted) | Table 1 (8 Rehab not yet Approved ha) | Table 1 (8 Spatial Submitted) | Table 1 (9 Rehab Commenced ha) | Table 1 (9 Spatial Submitted) | Table 1 (10 Proposed Disturbance ha) | Table 1 (10 Spatial Submitted) | Table 1 (11 Rehab for Certification ha) | Table 1 (11 Spatial Submitted) | Table 1 (12 Rehab not for Certification ha) | Table 1 (12 Spatial Submitted) | Table 1 (13 Rehab to Commence ha) | Table 1 (13 Spatial Submitted) | 5. Has there been a change to the carrying out of the resource activity that may affect the estimated rehabilitation cost (ERC) decision for the activity? | 6. Has the required GIS Spatial information been submitted in accordance with an approved PRC Plan? | 7. Have you complied with your PRCP schedule? | 8. Have you complied with all other conditions imposed on the PRCP schedule? | 9. Are works related to any other rehabilitation or management milestones underway? | Table 2 (1 Total Area ha) | Table 2 (1 Spatial Submitted) | Table 2 (2 Total Disturbance ha) | Table 2 (2 Spatial Submitted) | Table 2 (3 Total Rehab Certified ha) | Table 2 (3 Spatial Submitted) | Table 2 (4 Total Rehab Completed ha) | Table 2 (4 Spatial Submitted) | Table 2 (5 Total Rehab Commenced ha) | Table 2 (5 Spatial Submitted) | Table 2 (6 Total Sufficient Improvement ha) | Table 2 (6 Spatial Submitted) | Table 2 (7 Total Improvement Commenced ha) | Table 2 (7 Spatial Submitted) | Table 2 (8 Area Disturbed ha) | Table 2 (8 Spatial Submitted) | Table 2 (9 Approved Progressive Certification ha) | Table 2 (9 Spatial Submitted) | Table 2 (10 Rehab not yet Approved ha) | Table 2 (10 Spatial Submitted) | Table 2 (11 Rehab Commenced ha) | Table 2 (11 Spatial Submitted) | Table 2 (12 Sufficient Improvement ha) | Table 2 (12 Spatial Submitted) | Table 2 (13 Improvement Commenced ha) | Table 2 (13 Spatial Submitted) | Table 2 (14 Proposed Disturbance ha) | Table 2 (14 Spatial Submitted) | Table 2 (15 Rehab for Certification ha) | Table 2 (15 Spatial Submitted) | Table 2 (16 Rehab not for Certification ha) | Table 2 (16 Spatial Submitted) | Table 2 (17 Rehab to Commence ha) | Table 2 (17 Spatial Submitted) | Table 2 (18 Proposed Sufficient Improvement ha) | Table 2 (18 Spatial Submitted) | Table 2 (19 Improvement to Commence ha) | Table 2 (19 Spatial Submitted) | Signatory Name | Signatory Position | Date
RET-100039341 | 2020-01-01 | 2020-12-31 | 2021-04-01 | Completed | MT CUTHBERT RESOURCES PTY LTD | EPML00863313 | Resource Activity | Site-specific | MT CUTHBERT RESOURCES PTY LTD; | Minerals | Ancillary 31 - Mineral processing, 2(a) - Processing, in a year, the following quantities of mineral products, other than coke - 1000t to 100,000t; Ancillary 62 - Resource recovery and transfer facility operation, 1(c) - Operating a facility for receiving and sorting, dismantling, baling or temporarily storing category 2 regulated waste; Ancillary 08 - Chemical Storage, 5 - storing 200 cubic metres or more of chemicals that are liquids, other than chemicals mentioned in items 1 to 3, under subsection (1)(d); Ancillary 08 - Chemical Storage, 3 - Storing more than 500 cubic metres of chemicals of class C1 or C2 combustible liquids under AS 1940 or dangerous goods class 3 under subsection (1)(c); Ancillary 15 - Fuel burning, Using fuel burning equipment that is capable of burning at least 500kg of fuel in an hour; Schedule 3, 17 - Mining copper ore; Ancillary 60 - Waste disposal, 2(a) - Operating a facility for disposing of, in a year, the following quantity of waste mentioned in subsection (1)(b) - less than 2000t; Ancillary 62 - Resource recovery and transfer facility operation, 1(d) - Operating a facility for receiving and sorting, dismantling, baling or temporarily storing category 1 regulated waste; Ancillary 60 - Waste disposal, 1(d) - Operating a facility for disposing of, in a year, the following quantity of waste mentioned in subsection (1)(a) - more than 200,000t; Ancillary 63 - Sewage Treatment, 1(b-i) - Operating sewage treatment works, other than no-release works, with a total daily peak design capacity of more than 100 but not more than 1500EP if treated effluent is discharged from the works to an infiltration trench or through an irrigation scheme; | ML2705 THREE RIVERS 4824; ML90090 THREE RIVERS 4824; ML2747 THREE RIVERS 4824; ML2515 THREE RIVERS 4824; ML90066 MOUNT ISA 4825; ML90141 THREE RIVERS 4824; ML2784 THREE RIVERS 4824; ML2514 THREE RIVERS 4824; ML2494 THREE RIVERS 4824; ML90141 THREE RIVERS 4824; ML2784 THREE RIVERS 4824; ML90141 THREE RIVERS 4824; ML90066 MOUNT ISA 4825; ML2705 THREE RIVERS 4824; ML100152 THREE RIVERS 4824; ML7520 THREE RIVERS 4824; ML100152 THREE RIVERS 4824; ML100152 THREE RIVERS 4824; ML90066 MOUNT ISA 4825; ML90154 THREE RIVERS 4824; ML2708 THREE RIVERS 4824; ML2715 THREE RIVERS 4824; ML2706 THREE RIVERS 4824; ML2514 THREE RIVERS 4824; ML2705 THREE RIVERS 4824; ML90066 MOUNT ISA 4825; ML2494 THREE RIVERS 4824; ML7520 THREE RIVERS 4824; ML2784 THREE RIVERS 4824; ML90141 THREE RIVERS 4824; ML2747 THREE RIVERS 4824; ML90091 THREE RIVERS 4824; ML90142 THREE RIVERS 4824; ML90101 THREE RIVERS 4824; ML100152 THREE RIVERS 4824; ML2715 THREE RIVERS 4824; ml2492 THREE RIVERS 4824; ML2708 THREE RIVERS 4824; ML2635 THREE RIVERS 4824; ML90066 MOUNT ISA 4825; ml2492 THREE RIVERS 4824; ML90092 THREE RIVERS 4824; ML90142 THREE RIVERS 4824; ML2784 THREE RIVERS 4824; ML100152 THREE RIVERS 4824; ML2784 THREE RIVERS 4824; ML90066 MOUNT ISA 4825; ML2635 THREE RIVERS 4824; ML90141 THREE RIVERS 4824; ML2748 THREE RIVERS 4824; ML7520 THREE RIVERS 4824; ML90092 THREE RIVERS 4824; ML100152 THREE RIVERS 4824; ML2705 THREE RIVERS 4824; ML2747 THREE RIVERS 4824; ML2706 THREE RIVERS 4824; ML2514 THREE RIVERS 4824; ML2494 THREE RIVERS 4824; ML2636 THREE RIVERS 4824; ML90091 THREE RIVERS 4824; ML2708 THREE RIVERS 4824; ML2715 THREE RIVERS 4824; ML90142 THREE RIVERS 4824; ML2705 THREE RIVERS 4824; ML2494 THREE RIVERS 4824; ML2708 THREE RIVERS 4824; ML2514 THREE RIVERS 4824; ML2748 THREE RIVERS 4824; ML2494 THREE RIVERS 4824; ML90090 THREE RIVERS 4824; ML7520 THREE RIVERS 4824; ML90091 THREE RIVERS 4824; ML2635 THREE RIVERS 4824; ML2784 THREE RIVERS 4824; ML90101 THREE RIVERS 4824; ml2492 THREE RIVERS 4824; ML2636 THREE RIVERS 4824; ML2708 THREE RIVERS 4824; ML2635 THREE RIVERS 4824; ML90154 THREE RIVERS 4824; ML2715 THREE RIVERS 4824; ML90101 THREE RIVERS 4824; ML2706 THREE RIVERS 4824; ML2706 THREE RIVERS 4824; ML90090 THREE RIVERS 4824; ml2492 THREE RIVERS 4824; ML90066 MOUNT ISA 4825; ML7520 THREE RIVERS 4824; ML2748 THREE RIVERS 4824; ML90154 THREE RIVERS 4824; ML90141 THREE RIVERS 4824; ML2636 THREE RIVERS 4824; ML2515 THREE RIVERS 4824; ML90142 THREE RIVERS 4824; ML2705 THREE RIVERS 4824; ML2708 THREE RIVERS 4824; ML2715 THREE RIVERS 4824; ML90091 THREE RIVERS 4824; ML90091 THREE RIVERS 4824; ML2706 THREE RIVERS 4824; ML90092 THREE RIVERS 4824; ML2706 THREE RIVERS 4824; ML2494 THREE RIVERS 4824; ML100152 THREE RIVERS 4824; ml2492 THREE RIVERS 4824; ML90091 THREE RIVERS 4824; ML2748 THREE RIVERS 4824; ML90154 THREE RIVERS 4824; ML90142 THREE RIVERS 4824; ML90090 THREE RIVERS 4824; ML2715 THREE RIVERS 4824; ML2635 THREE RIVERS 4824; ML2635 THREE RIVERS 4824; ML90141 THREE RIVERS 4824; ML2515 THREE RIVERS 4824; ML2514 THREE RIVERS 4824; ML2636 THREE RIVERS 4824; ML90142 THREE RIVERS 4824; ML90101 THREE RIVERS 4824; ML90066 MOUNT ISA 4825; ML2515 THREE RIVERS 4824; ML90091 THREE RIVERS 4824; ML2706 THREE RIVERS 4824; ML2636 THREE RIVERS 4824; ML90142 THREE RIVERS 4824; ML2715 THREE RIVERS 4824; ML100152 THREE RIVERS 4824; ML2515 THREE RIVERS 4824; ML2784 THREE RIVERS 4824; ML100152 THREE RIVERS 4824; ml2492 THREE RIVERS 4824; ml2492 THREE RIVERS 4824; ml2492 THREE RIVERS 4824; ML90141 THREE RIVERS 4824; ML2494 THREE RIVERS 4824; ML2636 THREE RIVERS 4824; ML2747 THREE RIVERS 4824; ML90141 THREE RIVERS 4824; ML2706 THREE RIVERS 4824; ML2748 THREE RIVERS 4824; ML2784 THREE RIVERS 4824; ML90092 THREE RIVERS 4824; ML90090 THREE RIVERS 4824; ML2515 THREE RIVERS 4824; ML90101 THREE RIVERS 4824; ML90142 THREE RIVERS 4824; ML90090 THREE RIVERS 4824; ML90090 THREE RIVERS 4824; ML2494 THREE RIVERS 4824; ML2705 THREE RIVERS 4824; ML90101 THREE RIVERS 4824; ML90092 THREE RIVERS 4824; ML2494 THREE RIVERS 4824; ML100152 THREE RIVERS 4824; ML90154 THREE RIVERS 4824; ML90101 THREE RIVERS 4824; ML2494 THREE RIVERS 4824; ML2708 THREE RIVERS 4824; ML2706 THREE RIVERS 4824; ML90091 THREE RIVERS 4824; ML90101 THREE RIVERS 4824; ML2747 THREE RIVERS 4824; ML90101 THREE RIVERS 4824; ML90092 THREE RIVERS 4824; ML2747 THREE RIVERS 4824; ML2705 THREE RIVERS 4824; ML90090 THREE RIVERS 4824; ML90141 THREE RIVERS 4824; ML90142 THREE RIVERS 4824; ML90092 THREE RIVERS 4824; ML90154 THREE RIVERS 4824; ML2705 THREE RIVERS 4824; ML90154 THREE RIVERS 4824; ML2747 THREE RIVERS 4824; ML2636 THREE RIVERS 4824; ML90091 THREE RIVERS 4824; ML2636 THREE RIVERS 4824; ML7520 THREE RIVERS 4824; ML2748 THREE RIVERS 4824; ML2747 THREE RIVERS 4824; ML2636 THREE RIVERS 4824; ML2708 THREE RIVERS 4824; ml2492 THREE RIVERS 4824; ML2706 THREE RIVERS 4824; ML2635 THREE RIVERS 4824; ML90066 MOUNT ISA 4825; ML90154 THREE RIVERS 4824; ML2515 THREE RIVERS 4824; ML2708 THREE RIVERS 4824; ML90154 THREE RIVERS 4824; ML7520 THREE RIVERS 4824; ML90090 THREE RIVERS 4824; ML90154 THREE RIVERS 4824; ML90066 MOUNT ISA 4825; ML2715 THREE RIVERS 4824; ML7520 THREE RIVERS 4824; ML90101 THREE RIVERS 4824; ML2514 THREE RIVERS 4824; ML2514 THREE RIVERS 4824; ML90092 THREE RIVERS 4824; ML2748 THREE RIVERS 4824; ML2784 THREE RIVERS 4824; ML2635 THREE RIVERS 4824; ml2492 THREE RIVERS 4824; ML90142 THREE RIVERS 4824; ML2514 THREE RIVERS 4824; ML2515 THREE RIVERS 4824; ML2784 THREE RIVERS 4824; ML2747 THREE RIVERS 4824; ML2747 THREE RIVERS 4824; ML7520 THREE RIVERS 4824; ML2636 THREE RIVERS 4824; ML2514 THREE RIVERS 4824; ML2515 THREE RIVERS 4824; ML2748 THREE RIVERS 4824; ML90092 THREE RIVERS 4824; ML2514 THREE RIVERS 4824; ML2515 THREE RIVERS 4824; ML2708 THREE RIVERS 4824; ML90091 THREE RIVERS 4824; ML90090 THREE RIVERS 4824; ML2748 THREE RIVERS 4824; ML2715 THREE RIVERS 4824; ML2635 THREE RIVERS 4824; ML2748 THREE RIVERS 4824; ML7520 THREE RIVERS 4824; ML2715 THREE RIVERS 4824; ML90092 THREE RIVERS 4824; ML2705 THREE RIVERS 4824; ML2635 THREE RIVERS 4824; | A resource activity without an approved Progressive Rehabilitation and Closure Plan (PRCP) schedule – Only complete sections 1 and 3 of this form. | No | No | I/We have submitted GIS spatial information, which represents the onsite disturbance and rehabilitation within Table 1.; Spatial information has been submitted via the department’s spatial information submission inbox - spatialsubmit@des.qld.gov.au.; GIS spatial information has been prepared in accordance with the department’s Guideline - Spatial Information Submission (ESR/2018/4337), specifically Attachment 2 - Annual returns – shapefile attributes and submission requirements.; I/We have provided a summary of the onsite disturbance and rehabilitation within Table 1.; Yes | No | 1214.6400 | N/A | 181.8000 | N/A | 0.0000 | N/A | 0.0000 | N/A | 0.0000 | N/A | 0.0000 | N/A | 0.0000 | N/A | 0.0000 | N/A | 0.0000 | N/A | 0.0000 | N/A | 0.0000 | N/A | 0.0000 | N/A | 0.0000 | N/A | [43 empty] | Nikki Graetz | Tenement Manager | 01/04/2021

## Q7 Details
Return Reference | Period Start | Period End | Annual Return Due Date | Status | Permit Reference | Q7. Compliance with PRCP Schedule? | Q7. Compliant - Improvement Area | Q7. Compliant - Milestone Reference | Q7. Compliant - Area Required ha | Q7. Compliant - Area Completed ha | Q7. Compliant - Actions Taken | Q7. Compliant - Effectiveness | Q7. Non Compliant - Improvement Area | Q7. Non Compliant - Milestone Reference | Q7. Non Compliant - Details

## Q8 Details
Return Reference | Period Start | Period End | Annual Return Due Date | Status | Permit Reference | Q8. Compliance with other conditions of PRCP? | Q8. Non Compliant - Condition Number | Q8. Non Compliant - Details

## Q9 Details
Return Reference | Period Start | Period End | Annual Return Due Date | Status | Permit Reference | Q9. Other works underway? | Q9. Underway - Improvement Area | Q9. Underway - Milestone Reference | Q9. Underway - Completion Date | Q9. Underway - Area Completed ha | Q9. Underway - Actions Taken | Q9. Underway - Effectiveness