## Annual Returns Register
Return Reference | Period Start | Period End | Annual Return Due Date | Status | Customer Name | Permit Reference | Permit Type | Condition Type | Permit Holder(s) | Industry | Activities | Locations | PRCP / no PRCP | 1. Change may affect ERC decision? | 2. EA for eligible resource activity? | 3. EA for ineligible resource activity without approved PRCP schedule? | 4. EA for ineligible Resource Activity for CSG? | Table 1 (1 Total Area ha) | Table 1 (1 Spatial Submitted) | Table 1 (2 Total Disturbance ha) | Table 1 (2 Spatial Submitted) | Table 1 (3 Total Rehab Certified ha) | Table 1 (3 Spatial Submitted) | Table 1 (4 Total Rehab Completed ha) | Table 1 (4 Spatial Submitted) | Table 1 (5 Total Rehab Commenced ha) | Table 1 (5 Spatial Submitted) | Table 1 (6 Area Disturbed ha) | Table 1 (6 Spatial Submitted) | Table 1 (7 Approved Progressive Certification ha) | Table 1 (7 Spatial Submitted) | Table 1 (8 Rehab not yet Approved ha) | Table 1 (8 Spatial Submitted) | Table 1 (9 Rehab Commenced ha) | Table 1 (9 Spatial Submitted) | Table 1 (10 Proposed Disturbance ha) | Table 1 (10 Spatial Submitted) | Table 1 (11 Rehab for Certification ha) | Table 1 (11 Spatial Submitted) | Table 1 (12 Rehab not for Certification ha) | Table 1 (12 Spatial Submitted) | Table 1 (13 Rehab to Commence ha) | Table 1 (13 Spatial Submitted) | 5. Has there been a change to the carrying out of the resource activity that may affect the estimated rehabilitation cost (ERC) decision for the activity? | 6. Has the required GIS Spatial information been submitted in accordance with an approved PRC Plan? | 7. Have you complied with your PRCP schedule? | 8. Have you complied with all other conditions imposed on the PRCP schedule? | 9. Are works related to any other rehabilitation or management milestones underway? | Table 2 (1 Total Area ha) | Table 2 (1 Spatial Submitted) | Table 2 (2 Total Disturbance ha) | Table 2 (2 Spatial Submitted) | Table 2 (3 Total Rehab Certified ha) | Table 2 (3 Spatial Submitted) | Table 2 (4 Total Rehab Completed ha) | Table 2 (4 Spatial Submitted) | Table 2 (5 Total Rehab Commenced ha) | Table 2 (5 Spatial Submitted) | Table 2 (6 Total Sufficient Improvement ha) | Table 2 (6 Spatial Submitted) | Table 2 (7 Total Improvement Commenced ha) | Table 2 (7 Spatial Submitted) | Table 2 (8 Area Disturbed ha) | Table 2 (8 Spatial Submitted) | Table 2 (9 Approved Progressive Certification ha) | Table 2 (9 Spatial Submitted) | Table 2 (10 Rehab not yet Approved ha) | Table 2 (10 Spatial Submitted) | Table 2 (11 Rehab Commenced ha) | Table 2 (11 Spatial Submitted) | Table 2 (12 Sufficient Improvement ha) | Table 2 (12 Spatial Submitted) | Table 2 (13 Improvement Commenced ha) | Table 2 (13 Spatial Submitted) | Table 2 (14 Proposed Disturbance ha) | Table 2 (14 Spatial Submitted) | Table 2 (15 Rehab for Certification ha) | Table 2 (15 Spatial Submitted) | Table 2 (16 Rehab not for Certification ha) | Table 2 (16 Spatial Submitted) | Table 2 (17 Rehab to Commence ha) | Table 2 (17 Spatial Submitted) | Table 2 (18 Proposed Sufficient Improvement ha) | Table 2 (18 Spatial Submitted) | Table 2 (19 Improvement to Commence ha) | Table 2 (19 Spatial Submitted) | Signatory Name | Signatory Position | Date
RET-100795764 | 2024-01-01 | 2024-12-31 | 2025-04-01 | Completed | Peabody (Burton Coal) Pty Ltd | EPML00879213 | Resource Activity | Site-specific | Peabody (Burton Coal) Pty Ltd; | Coal | Schedule 3, 13 - Mining black coal; Ancillary 63 - Sewage Treatment, 1(b-i) - Operating sewage treatment works, other than no-release works, with a total daily peak design capacity of more than 100 but not more than 1500EP if treated effluent is discharged from the works to an infiltration trench or through an irrigation scheme; Ancillary 62 - Resource recovery and transfer facility operation, 1(c) - Operating a facility for receiving and sorting, dismantling, baling or temporarily storing category 2 regulated waste; Ancillary 60 - Waste disposal, 2(c) - Operating a facility for disposing of, in a year, the following quantity of waste mentioned in subsection (1)(b) - more than 5000t but not more than 10,000t; Schedule 3, 09 - A mining activity involving drilling, costeaning, pitting or carrying out geological surveys causing significant disturbance; | ML70259 BURTON 4742; ML70259 BURTON 4742; ML70259 BURTON 4742; ML70252 BURTON 4742; ML70252 MORANBAH 4744; ML70259 BURTON 4742; ML70258 BURTON 4742; MDL308 BURTON 4742; ML70252 BURTON 4742; ML70252 MORANBAH 4744; ML70258 BURTON 4742; ML70258 BURTON 4742; ML70252 BURTON 4742; ML70252 MORANBAH 4744; ML70256 MORANBAH 4744; ML70256 BURTON 4742; MDL308 BURTON 4742; ML70252 BURTON 4742; ML70252 MORANBAH 4744; ML70259 BURTON 4742; MDL308 BURTON 4742; ML70256 MORANBAH 4744; ML70256 BURTON 4742; ML70258 BURTON 4742; ML70252 BURTON 4742; ML70252 MORANBAH 4744; ML70256 MORANBAH 4744; ML70256 BURTON 4742; ML70256 MORANBAH 4744; ML70256 BURTON 4742; MDL308 BURTON 4742; ML70256 MORANBAH 4744; ML70256 BURTON 4742; ML70258 BURTON 4742; MDL308 BURTON 4742; | A resource activity with an approved (PRCP) schedule – Only complete sections 2 and 3 of this form. | [30 empty] | No | I/We have submitted GIS spatial information, which represents the onsite disturbance, rehabilitation and improvement within Table 2; Spatial information has been submitted via the department’s spatial information submission inbox - spatialsubmit@des.qld.gov.au.; GIS spatial information has been prepared in accordance with the department’s Guideline - Spatial Information Submission (ESR/2018/4337), specifically Attachment 2 - Annual returns – shapefile attributes and submission requirements.; I/We have provided a summary of the onsite disturbance and rehabilitation within Table 2; Yes | Yes | Yes | Yes | 5535.7500 | Yes | 228.7000 | Yes | 0.0000 | N/A | 1332.6000 | Yes | 118.8000 | Yes | 9.4000 | Yes | 8.7000 | Yes | 0.0000 | N/A | 0.0000 | N/A | 0.0000 | Yes | 42.3000 | Yes | 0.0000 | N/A | 18.1000 | Yes | 0.0000 | N/A | 0.0000 | N/A | 29.0000 | Yes | 0.0000 | N/A | 0.0000 | N/A | 0.0000 | N/A | John Michael Anger | Director | 14/03/2025

## Q7 Details
Return Reference | Period Start | Period End | Annual Return Due Date | Status | Permit Reference | Q7. Compliance with PRCP Schedule? | Q7. Compliant - Improvement Area | Q7. Compliant - Milestone Reference | Q7. Compliant - Area Required ha | Q7. Compliant - Area Completed ha | Q7. Compliant - Actions Taken | Q7. Compliant - Effectiveness | Q7. Non Compliant - Improvement Area | Q7. Non Compliant - Milestone Reference | Q7. Non Compliant - Details
RET-100795764 | 2024-01-01 | 2024-12-31 | 2025-04-01 | Completed | EPML00879213 | Yes | RA2 | RM3 | 51.50 | 84.00 | RM3 completed | Effective
RET-100795764 | 2024-01-01 | 2024-12-31 | 2025-04-01 | Completed | EPML00879213 | Yes | RA3 | RM1 and RM3 | 15.50 | 22.10 | RM1 and RM3 completed | Effective
RET-100795764 | 2024-01-01 | 2024-12-31 | 2025-04-01 | Completed | EPML00879213 | Yes | RA6 | RM3 | 259.50 | 257.90 | RM3 completed | Effective
RET-100795764 | 2024-01-01 | 2024-12-31 | 2025-04-01 | Completed | EPML00879213 | Yes | RA6 | RM4 | 207.20 | 228.60 | RM4 completed | Effective
RET-100795764 | 2024-01-01 | 2024-12-31 | 2025-04-01 | Completed | EPML00879213 | Yes | RA6 | RM5 | 207.20 | 240.60 | RM5 completed | Effective
RET-100795764 | 2024-01-01 | 2024-12-31 | 2025-04-01 | Completed | EPML00879213 | Yes | RA7 | RM1 and RM3 | 43.10 | 37.10 | RM1 and RM3 completed | Effective
RET-100795764 | 2024-01-01 | 2024-12-31 | 2025-04-01 | Completed | EPML00879213 | Yes | RA7 | RM4 and RM5 | 18.80 | 30.70 | RM4 and RM5 completed | Effective
RET-100795764 | 2024-01-01 | 2024-12-31 | 2025-04-01 | Completed | EPML00879213 | Yes | IA4 | MM1 and MM2 | 28.10 | 28.10 | MM1 and MM2 completed | Effective
RET-100795764 | 2024-01-01 | 2024-12-31 | 2025-04-01 | Completed | EPML00879213 | Yes | IA5 | MM1 and MM2 | 75.40 | 66.50 | MM1 and MM2 completed | Effective

## Q8 Details
Return Reference | Period Start | Period End | Annual Return Due Date | Status | Permit Reference | Q8. Compliance with other conditions of PRCP? | Q8. Non Compliant - Condition Number | Q8. Non Compliant - Details
RET-100795764 | 2024-01-01 | 2024-12-31 | 2025-04-01 | Completed | EPML00879213 | Yes

## Q9 Details
Return Reference | Period Start | Period End | Annual Return Due Date | Status | Permit Reference | Q9. Other works underway? | Q9. Underway - Improvement Area | Q9. Underway - Milestone Reference | Q9. Underway - Completion Date | Q9. Underway - Area Completed ha | Q9. Underway - Actions Taken | Q9. Underway - Effectiveness
RET-100795764 | 2024-01-01 | 2024-12-31 | 2025-04-01 | Completed | EPML00879213 | Yes | RA2 | RM3 | Dec 10 2025 12:00AM | 63.80 | RM3 completed | Effective
RET-100795764 | 2024-01-01 | 2024-12-31 | 2025-04-01 | Completed | EPML00879213 | Yes | RA2 | RM4 | Dec 10 2025 12:00AM | 51.50 | RM4 completed | Effective
RET-100795764 | 2024-01-01 | 2024-12-31 | 2025-04-01 | Completed | EPML00879213 | Yes | RA2 | RM5 | Dec 10 2025 12:00AM | 51.50 | RM5 completed | Effective
RET-100795764 | 2024-01-01 | 2024-12-31 | 2025-04-01 | Completed | EPML00879213 | Yes | RA3 | RM4 | Dec 10 2025 12:00AM | 15.50 | RM4 completed | Effective
RET-100795764 | 2024-01-01 | 2024-12-31 | 2025-04-01 | Completed | EPML00879213 | Yes | RA3 | RM5 | Dec 10 2025 12:00AM | 15.50 | RM5 completed | Effective
RET-100795764 | 2024-01-01 | 2024-12-31 | 2025-04-01 | Completed | EPML00879213 | Yes | RA5 | RM8 | Dec 10 2025 12:00AM | 269.60 | RM8 completed | Effective
RET-100795764 | 2024-01-01 | 2024-12-31 | 2025-04-01 | Completed | EPML00879213 | Yes | RA6 | RM5 and RM5 | Dec 10 2025 12:00AM | 259.50 | RM4 and RM5 completed | Effective
RET-100795764 | 2024-01-01 | 2024-12-31 | 2025-04-01 | Completed | EPML00879213 | Yes | RA7 | RM4 and RM5 | Dec 10 2025 12:00AM | 43.10 | RM4 and RM5 completed | Effective