## Annual Returns Register
Return Reference | Period Start | Period End | Annual Return Due Date | Status | Customer Name | Permit Reference | Permit Type | Condition Type | Permit Holder(s) | Industry | Activities | Locations | PRCP / no PRCP | 1. Change may affect ERC decision? | 2. EA for eligible resource activity? | 3. EA for ineligible resource activity without approved PRCP schedule? | 4. EA for ineligible Resource Activity for CSG? | Table 1 (1 Total Area ha) | Table 1 (1 Spatial Submitted) | Table 1 (2 Total Disturbance ha) | Table 1 (2 Spatial Submitted) | Table 1 (3 Total Rehab Certified ha) | Table 1 (3 Spatial Submitted) | Table 1 (4 Total Rehab Completed ha) | Table 1 (4 Spatial Submitted) | Table 1 (5 Total Rehab Commenced ha) | Table 1 (5 Spatial Submitted) | Table 1 (6 Area Disturbed ha) | Table 1 (6 Spatial Submitted) | Table 1 (7 Approved Progressive Certification ha) | Table 1 (7 Spatial Submitted) | Table 1 (8 Rehab not yet Approved ha) | Table 1 (8 Spatial Submitted) | Table 1 (9 Rehab Commenced ha) | Table 1 (9 Spatial Submitted) | Table 1 (10 Proposed Disturbance ha) | Table 1 (10 Spatial Submitted) | Table 1 (11 Rehab for Certification ha) | Table 1 (11 Spatial Submitted) | Table 1 (12 Rehab not for Certification ha) | Table 1 (12 Spatial Submitted) | Table 1 (13 Rehab to Commence ha) | Table 1 (13 Spatial Submitted) | 5. Has there been a change to the carrying out of the resource activity that may affect the estimated rehabilitation cost (ERC) decision for the activity? | 6. Has the required GIS Spatial information been submitted in accordance with an approved PRC Plan? | 7. Have you complied with your PRCP schedule? | 8. Have you complied with all other conditions imposed on the PRCP schedule? | 9. Are works related to any other rehabilitation or management milestones underway? | Table 2 (1 Total Area ha) | Table 2 (1 Spatial Submitted) | Table 2 (2 Total Disturbance ha) | Table 2 (2 Spatial Submitted) | Table 2 (3 Total Rehab Certified ha) | Table 2 (3 Spatial Submitted) | Table 2 (4 Total Rehab Completed ha) | Table 2 (4 Spatial Submitted) | Table 2 (5 Total Rehab Commenced ha) | Table 2 (5 Spatial Submitted) | Table 2 (6 Total Sufficient Improvement ha) | Table 2 (6 Spatial Submitted) | Table 2 (7 Total Improvement Commenced ha) | Table 2 (7 Spatial Submitted) | Table 2 (8 Area Disturbed ha) | Table 2 (8 Spatial Submitted) | Table 2 (9 Approved Progressive Certification ha) | Table 2 (9 Spatial Submitted) | Table 2 (10 Rehab not yet Approved ha) | Table 2 (10 Spatial Submitted) | Table 2 (11 Rehab Commenced ha) | Table 2 (11 Spatial Submitted) | Table 2 (12 Sufficient Improvement ha) | Table 2 (12 Spatial Submitted) | Table 2 (13 Improvement Commenced ha) | Table 2 (13 Spatial Submitted) | Table 2 (14 Proposed Disturbance ha) | Table 2 (14 Spatial Submitted) | Table 2 (15 Rehab for Certification ha) | Table 2 (15 Spatial Submitted) | Table 2 (16 Rehab not for Certification ha) | Table 2 (16 Spatial Submitted) | Table 2 (17 Rehab to Commence ha) | Table 2 (17 Spatial Submitted) | Table 2 (18 Proposed Sufficient Improvement ha) | Table 2 (18 Spatial Submitted) | Table 2 (19 Improvement to Commence ha) | Table 2 (19 Spatial Submitted) | Signatory Name | Signatory Position | Date
RET-100550980 | 2023-01-01 | 2023-12-31 | 2024-04-01 | Completed | AEON MONTO EXPLORATION PTY LTD | EPSX00291513 | Resource Activity | Standard | AEON MONTO EXPLORATION PTY LTD; | Minerals | Non-Scheduled, Mining Activity - Exploration Permit Mineral (EPM); | EPM14628 COOMINGLAH FOREST 4630; EPM14628 COOMINGLAH 4630; EPM14628 LAWGI DAWES 4716; EPM14628 RAWBELLE 4630; | A resource activity without an approved Progressive Rehabilitation and Closure Plan (PRCP) schedule – Only complete sections 1 and 3 of this form. | No | I/We have provided a summary of the onsite disturbance and rehabilitation within Table 1.; Yes | No | No | 9959.0000 | N/A | 0.0000 | N/A | 0.0000 | N/A | 0.0000 | N/A | 0.0000 | N/A | 0.0000 | N/A | 0.0000 | N/A | 0.0000 | N/A | 0.0000 | N/A | 0.0000 | N/A | 0.0000 | N/A | 0.0000 | N/A | 0.0000 | N/A | [43 empty] | Paul Harris | Director | 28/03/2024

## Q7 Details
Return Reference | Period Start | Period End | Annual Return Due Date | Status | Permit Reference | Q7. Compliance with PRCP Schedule? | Q7. Compliant - Improvement Area | Q7. Compliant - Milestone Reference | Q7. Compliant - Area Required ha | Q7. Compliant - Area Completed ha | Q7. Compliant - Actions Taken | Q7. Compliant - Effectiveness | Q7. Non Compliant - Improvement Area | Q7. Non Compliant - Milestone Reference | Q7. Non Compliant - Details

## Q8 Details
Return Reference | Period Start | Period End | Annual Return Due Date | Status | Permit Reference | Q8. Compliance with other conditions of PRCP? | Q8. Non Compliant - Condition Number | Q8. Non Compliant - Details

## Q9 Details
Return Reference | Period Start | Period End | Annual Return Due Date | Status | Permit Reference | Q9. Other works underway? | Q9. Underway - Improvement Area | Q9. Underway - Milestone Reference | Q9. Underway - Completion Date | Q9. Underway - Area Completed ha | Q9. Underway - Actions Taken | Q9. Underway - Effectiveness