## Annual Returns Register
Return Reference | Period Start | Period End | Annual Return Due Date | Status | Customer Name | Permit Reference | Permit Type | Condition Type | Permit Holder(s) | Industry | Activities | Locations | PRCP / no PRCP | 1. Change may affect ERC decision? | 2. EA for eligible resource activity? | 3. EA for ineligible resource activity without approved PRCP schedule? | 4. EA for ineligible Resource Activity for CSG? | Table 1 (1 Total Area ha) | Table 1 (1 Spatial Submitted) | Table 1 (2 Total Disturbance ha) | Table 1 (2 Spatial Submitted) | Table 1 (3 Total Rehab Certified ha) | Table 1 (3 Spatial Submitted) | Table 1 (4 Total Rehab Completed ha) | Table 1 (4 Spatial Submitted) | Table 1 (5 Total Rehab Commenced ha) | Table 1 (5 Spatial Submitted) | Table 1 (6 Area Disturbed ha) | Table 1 (6 Spatial Submitted) | Table 1 (7 Approved Progressive Certification ha) | Table 1 (7 Spatial Submitted) | Table 1 (8 Rehab not yet Approved ha) | Table 1 (8 Spatial Submitted) | Table 1 (9 Rehab Commenced ha) | Table 1 (9 Spatial Submitted) | Table 1 (10 Proposed Disturbance ha) | Table 1 (10 Spatial Submitted) | Table 1 (11 Rehab for Certification ha) | Table 1 (11 Spatial Submitted) | Table 1 (12 Rehab not for Certification ha) | Table 1 (12 Spatial Submitted) | Table 1 (13 Rehab to Commence ha) | Table 1 (13 Spatial Submitted) | 5. Has there been a change to the carrying out of the resource activity that may affect the estimated rehabilitation cost (ERC) decision for the activity? | 6. Has the required GIS Spatial information been submitted in accordance with an approved PRC Plan? | 7. Have you complied with your PRCP schedule? | 8. Have you complied with all other conditions imposed on the PRCP schedule? | 9. Are works related to any other rehabilitation or management milestones underway? | Table 2 (1 Total Area ha) | Table 2 (1 Spatial Submitted) | Table 2 (2 Total Disturbance ha) | Table 2 (2 Spatial Submitted) | Table 2 (3 Total Rehab Certified ha) | Table 2 (3 Spatial Submitted) | Table 2 (4 Total Rehab Completed ha) | Table 2 (4 Spatial Submitted) | Table 2 (5 Total Rehab Commenced ha) | Table 2 (5 Spatial Submitted) | Table 2 (6 Total Sufficient Improvement ha) | Table 2 (6 Spatial Submitted) | Table 2 (7 Total Improvement Commenced ha) | Table 2 (7 Spatial Submitted) | Table 2 (8 Area Disturbed ha) | Table 2 (8 Spatial Submitted) | Table 2 (9 Approved Progressive Certification ha) | Table 2 (9 Spatial Submitted) | Table 2 (10 Rehab not yet Approved ha) | Table 2 (10 Spatial Submitted) | Table 2 (11 Rehab Commenced ha) | Table 2 (11 Spatial Submitted) | Table 2 (12 Sufficient Improvement ha) | Table 2 (12 Spatial Submitted) | Table 2 (13 Improvement Commenced ha) | Table 2 (13 Spatial Submitted) | Table 2 (14 Proposed Disturbance ha) | Table 2 (14 Spatial Submitted) | Table 2 (15 Rehab for Certification ha) | Table 2 (15 Spatial Submitted) | Table 2 (16 Rehab not for Certification ha) | Table 2 (16 Spatial Submitted) | Table 2 (17 Rehab to Commence ha) | Table 2 (17 Spatial Submitted) | Table 2 (18 Proposed Sufficient Improvement ha) | Table 2 (18 Spatial Submitted) | Table 2 (19 Improvement to Commence ha) | Table 2 (19 Spatial Submitted) | Signatory Name | Signatory Position | Date
RET-100342691 | 2022-01-01 | 2022-12-31 | 2023-04-01 | Completed | NC COAL COMPANY PTY LIMITED | EPML00332013 | Resource Activity | Site-specific | NC COAL COMPANY PTY LIMITED; | Coal | Schedule 3, 13 - Mining black coal; Ancillary 31 - Mineral processing, 2(b) - Processing, in a year, the following quantities of mineral products, other than coke - more than 100,000t; Ancillary 63 - Sewage Treatment, 1(b-i) - Operating sewage treatment works, other than no-release works, with a total daily peak design capacity of more than 100 but not more than 1500EP if treated effluent is discharged from the works to an infiltration trench or through an irrigation scheme; | ML1005 COLLINSVILLE 4804; ML1005 SPRINGLANDS 4804; ML1005 SCOTTVILLE 4804; ML1005 COLLINSVILLE 4804; ML1005 SPRINGLANDS 4804; ML1005 SCOTTVILLE 4804; ML1005 COLLINSVILLE 4804; ML1005 SPRINGLANDS 4804; ML1005 SCOTTVILLE 4804; ML1009 SPRINGLANDS 4804; ML1009 COLLINSVILLE 4804; ML1009 SCOTTVILLE 4804; ML1009 SPRINGLANDS 4804; ML1009 COLLINSVILLE 4804; ML1009 SCOTTVILLE 4804; ML1009 SPRINGLANDS 4804; ML1009 COLLINSVILLE 4804; ML1009 SCOTTVILLE 4804; ML1006 COLLINSVILLE 4804; ML1006 COLLINSVILLE 4804; ML1006 COLLINSVILLE 4804; ML1064 SPRINGLANDS 4804; ML1064 SPRINGLANDS 4804; ML1064 SPRINGLANDS 4804; ML10111 SPRINGLANDS 4804; ML10111 SPRINGLANDS 4804; ML10111 SPRINGLANDS 4804; ML10333 SPRINGLANDS 4804; ML10333 SPRINGLANDS 4804; ML1008 SPRINGLANDS 4804; ML1008 SCOTTVILLE 4804; ML1008 SPRINGLANDS 4804; ML1008 SCOTTVILLE 4804; ML1008 SPRINGLANDS 4804; ML1008 SCOTTVILLE 4804; ML10333 SPRINGLANDS 4804; ML1015 COLLINSVILLE 4804; ML1015 SCOTTVILLE 4804; ML1015 COLLINSVILLE 4804; ML1015 SCOTTVILLE 4804; ML1015 COLLINSVILLE 4804; ML1015 SCOTTVILLE 4804; ML1037 SPRINGLANDS 4804; ML1037 SPRINGLANDS 4804; ML1037 SPRINGLANDS 4804; ML10250 SPRINGLANDS 4804; ML10250 SPRINGLANDS 4804; ML10250 SPRINGLANDS 4804; ML1007 SPRINGLANDS 4804; ML1007 SCOTTVILLE 4804; ML1007 SPRINGLANDS 4804; ML1007 SCOTTVILLE 4804; ML1007 SPRINGLANDS 4804; ML1007 SCOTTVILLE 4804; | A resource activity without an approved Progressive Rehabilitation and Closure Plan (PRCP) schedule – Only complete sections 1 and 3 of this form. | No | No | I/We have submitted GIS spatial information, which represents the onsite disturbance and rehabilitation within Table 1.; Spatial information has been submitted via the department’s spatial information submission inbox - spatialsubmit@des.qld.gov.au.; GIS spatial information has been prepared in accordance with the department’s Guideline - Spatial Information Submission (ESR/2018/4337), specifically Attachment 2 - Annual returns – shapefile attributes and submission requirements.; I/We have provided a summary of the onsite disturbance and rehabilitation within Table 1.; Yes | No | 9512.8000 | N/A | 2004.4000 | Yes | 99.5000 | Yes | 1408.3000 | Yes | 0.0000 | Yes | 36.2000 | Yes | 0.0000 | Yes | 29.5000 | Yes | 0.0000 | Yes | 12.0000 |  | 0.0000 | Yes | 93.3000 | Yes | 0.0000 | Yes | [43 empty] | Henning Boshoff | E & C Manager | 16/03/2023

## Q7 Details
Return Reference | Period Start | Period End | Annual Return Due Date | Status | Permit Reference | Q7. Compliance with PRCP Schedule? | Q7. Compliant - Improvement Area | Q7. Compliant - Milestone Reference | Q7. Compliant - Area Required ha | Q7. Compliant - Area Completed ha | Q7. Compliant - Actions Taken | Q7. Compliant - Effectiveness | Q7. Non Compliant - Improvement Area | Q7. Non Compliant - Milestone Reference | Q7. Non Compliant - Details

## Q8 Details
Return Reference | Period Start | Period End | Annual Return Due Date | Status | Permit Reference | Q8. Compliance with other conditions of PRCP? | Q8. Non Compliant - Condition Number | Q8. Non Compliant - Details

## Q9 Details
Return Reference | Period Start | Period End | Annual Return Due Date | Status | Permit Reference | Q9. Other works underway? | Q9. Underway - Improvement Area | Q9. Underway - Milestone Reference | Q9. Underway - Completion Date | Q9. Underway - Area Completed ha | Q9. Underway - Actions Taken | Q9. Underway - Effectiveness